***Basic scheduling***

|  |  |  |
| --- | --- | --- |
| The tasks | Duration | Predecessors |
| A | 3 |  |
| B | 4 | A |
| C | 2 | A |
| D | 5 | B |
| E | 1 | C |
| F | 2 | C |
| G | 4 | D, and E |
| H | 3 | F, and G |

The duration is 19 days